## Status Report
Project Name | Schemer |  | Date |  | 2023-03-18 | Project Manager |  | Adam Ryan
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Develop a website for Fiction writers to create their stories. The website will have a text editor as well as Bio Pages to keep track of the characters and settings in their novel. The text and bios will be linked for the entities in the story. |  |  |  | Determine Project Requirements |  | 100% | Complete |  | 2023-02-11
|  |  |  | Determine Data Model & Languages |  | 100% | Complete |  | 2023-02-18
|  |  |  | Independent Development |  | 70% | On Track
|  |  |  | Connect Client and Server |  | 40% | On Track
|  |  |  | Full Testing |  | 10% | On Track
|  |  |  | Add additional features |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Prepared front-end for demo, added authentication integrations to front-end, small code cleanup. | [5 empty] | Hookup endpoints for all other data. Create a dashboard for multiple stories. Create test cases for system functions.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Emma Harrington | FE / UX | 5 | Risk | Creating an environment to test functions may be difficult. Will it interfere with actual endpoints? Still have yet to compile the Front end and upload it to a publicly accessible place.
Adam Ryan | Project Manager / FE | 5
Eric Spencer | Chief Architect | 5
Jake Christensen | FE/BE Developer | 6 | Issue | .
Drew Moss | BE Developer | 5
Marcus Tracy | BE Developer | 5
Total |  | 31

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task